## Slide 1: BITS Pilani presentation
K.Anantharaman
kanantharaman@wilp.bits-pilani.ac.in
28/10/23
SE ZG544 S1-23-24 Agile software processes

## Slide 2
SE CZ 544 , Agile software processes
CS-10 – Agile Metrics and Tools
28/10/23
SE ZG544 S1-23-24 Agile software processes

## Slide 3
Examples:
  Velocity, Lead time, Cycle time, Charts, Escape defects and so on.
Helps to assess the quality of a product and track team performance.
The Concept:
  Define Metrics that can be used by Agile teams and Team management, Agile metrics that matter.
The Opportunity
  Reduced costs, Increase Product Quality, Increased team satisfaction
The Potential
  Auto Generate using exposed APIs provided by various PM tools.
Agile Metrics
28/10/23
SE ZG544 S1-23-24 Agile software processes
Source: Prachi Maini, Manager, QA Engineering, Morningstar, Inc.

## Slide 4
Quantitative Metric
  Measurement number: Lead time, Number of defects ….
Qualitative Metric
  Based on subjective opinion: Maintainability, Team happiness index …
Quantitative & Qualitative Metric
28/10/23
SE ZG544 S1-23-24 Agile software processes
Source:https://www.infoq.com/articles/metrics-agile-teams/

## Slide 5
Example: Lead time is a useful quantitative statistic for evaluating team performance.
Determinant metrics:
  A set of measurements related to a specific measurement
  Associated metrics:
  Flow efficiency (wait time)
  Speeding tickets(%), ( Tickets moves through multiple statuses)
  Total sprint completion (Committed vs Actual Story points)
  Defects returned from QA(%)
  Escape defects(%)
  Bug fixing Vs working on feature (% time)
An example Quantitative Metric
28/10/23
SE ZG544 S1-23-24 Agile software processes
Ready
Progress
Done
Lead time
Cycle Time

## Slide 6
An example - Good Qualitative Agile Metrics: Team Adoption to Agile
28/10/23
SE ZG544 S1-23-24 Agile software processes
https://www.crisp.se/wp-content/uploads/2012/05/Scrum-checklist.pdf
Sprint N
Sprint N+1
Green: It worked for the team.
Orange: Room for improvement.
Red: Didn’t apply or the practice is failing

## Slide 7
WHAT ARE SOME TRENDS OF BURNDOWN CHARTS AND WHAT DO THE PATTERNS INDICATE?
28/10/23
SE ZG544 S1-23-24 Agile software processes
Uptick: New tasks/Stories added. Issue if continues.
Flatline: Multiple reasons. Impediments, Task/Stories added at the same rate as work complete.
Sharpdrop: Team not updating the chart/ Pointed removed
Perfect line: Team trying to align with expectations

## Slide 8
Capacity | Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78
Team Size | 8 | 8 | 8 | 8 | 8
Available Days | 80 | 80 | 80 | 80 | 80
Unavailable Days | 10 | 12 | 11 | 5 | 0
Net Days (Capacity) | 70 | 68 | 69 | 75 | 80
Velocity |  |  |  |  | 
Total Points Completed | 73 | 87 | 75 | 51 | 125
Adjusted Velocity | 83 | 102 | 87 | 54 | 125
Avg Velocity (Last 3 Sprints) | 88 | 90 | 91 | 81 | 89
Velocity
Source: Prachi Maini, Manager, QA Engineering, Morningstar, Inc.

## Slide 9
Bug counts
28/10/23
SE ZG544 S1-23-24 Agile software processes
Source: Agile Metrics in Action: How to measure and improve team performance by Christopher W. H. Davis , Published by Manning Publications, 2015

## Slide 10
Metrics never convey the whole picture. Management by metrics and dashboards needs to be supplemented with management by context and conversations.
Stop measurements that lead to counterproductive behavior and stop at measurements (i.e., don’t continue to targets) that lead to desired behavior.
Prefer outcome-oriented metrics to activity-oriented ones. Prefer aggregate metrics to fine-grained ones.
Get comfortable with lagging (or trailing) indicators. When fast feedback is available, lagging indicators are a reliable alternative to speculative leading indicators.
Summary
28/10/23
SE ZG544 S1-23-24 Agile software processes

## Slide 11: Quiz

## Slide 12: Cumulative flow diagram Q1: What to Watch for?
1
2
3
4

## Slide 13: Project Progress: Q2: What to Watch for?
SE ZG544 S1-23-24 Agile software processes
28/10/23
Chart: Committed vs Completed
| Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78
Committed | 148 | 105 | 98 | 53 | 154
Completed | 74 | 87 | 75 | 51 | 125
Burndown chart
Chart: Work done by Tech Category
| Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78
Other | 23 | 10 | 0 | 0 | 0
Maintenance | 15 | 16 | 18 | 12 | 14
New Product Development | 57 | 71 | 60 | 70 | 50
Client Customization | 5 | 6 | 10 | 2 | 12

## Slide 14: Q2
SE ZG544 S1-23-24 Agile software processes
28/10/23
How do you connect this measure to production defects?

## Slide 15: Q3
SE ZG544 S1-23-24 Agile software processes
28/10/23
Chart: Net Open Bugs
| Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78
Net Open Bugs | 438 | 444 | 461 | 464 | 466
Chart: 
| Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78
Regression | 16 | 24 | 16 | 38 | 40
Feature | 68 | 36 | 33 | 41 | 17
Chart: 
| Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78
QA | 25 | 30 | 28 | 30 | 26
Stg | 5 | 4 | 4 | 4 | 3
UAT | 1 | 3 | 1 | 3 | 1
Prod | 2 | 1 | 2 | 1 | 8

## Slide 16
Additional Notes - Measuring Agile Performance
28/10/23
SE ZG544 S1-23-24 Agile software processes

## Slide 17
Good Quantitative Agile Metrics: Lead Time and Cycle Time
28/10/23
SE ZG544 S1-23-24 Agile software processes
Important to measure the things that drive/determine Lead Times.
Levers that teams can actively (e.g. determinant metrics like Flow Efficiency).

## Slide 18
Simple SI metrics | Metric | Comment
Overall SI goal metrics | Lead Time, Cycle Time | Good measures of overall Time to Value
Determinant metrics: |  | 
Best practice and tool use | Speeding tickets (%) | Tickets that have been moved through multiple Statuses (e.g. in Jira) after the event (so there is no real visibility of workflow stages)
Timing accuracy | Total Sprint Completion (%) | Percentage of completed story points for a given sprint(s). The factor takes into account story points added once a sprint has started.
Most common and meaningful metrics for Team SI
28/10/23
SE ZG544 S1-23-24 Agile software processes
Source:https://www.infoq.com/articles/metrics-agile-teams/

## Slide 19
Most common and meaningful metrics for Team SI …
28/10/23
SE ZG544 S1-23-24 Agile software processes
Simple SI metrics | Metric | Comment
Productivity | Flow efficiency (%) | Percentage of time spent active versus inactive within a workflow
 | Return rate (%) | Percentage of tickets returned from QA (for whatever reason) during the dev process. This generates Rework.
 | % Time bug fixing (The ratio of fixing work to feature work.) | Percentage of time a team spends bug fixing versus feature contribution.
 | Number of defects escaping to production. | This is category of fixing the work.
Source:https://www.infoq.com/articles/metrics-agile-teams/

## Slide 20
Most common and meaningful metrics for Team SI …
28/10/23
SE ZG544 S1-23-24 Agile software processes
Simple SI metrics | Metric | Comment
Team Wellness | Team Happiness Team Sprint Effectiveness Rating | Self Assessment tests: Individual engineers polled each Sprint/cycle.
Source:https://www.infoq.com/articles/metrics-agile-teams/

## Slide 21
The philosophy of Continuous Improvement (CI) is central to Agile.
CI- should not be imposed and driven top-down – instead it should be led by Agile teams themselves, so Self-Improvement (SI) is a more suitable terminology.
SI is hard requires organization leadership long term support, recognition and suitable framework. Crucially,
  A set of meaningful and agreed Agile metrics to track performance improvement over time; and a means to surface these metrics in near real time, with minimum/no effort involved for the teams themselves.
  Keep metrics simple and deterministic ( no ambiguity).
  For each of these metrics, it is the trend that is important, not an absolute number. The trend will tell you if your attempts at improvement are having an effect.
The Importance of Metrics to Agile Teams
28/10/23
SE ZG544 S1-23-24 Agile software processes

## Slide 22
An example cumulative flow diagram showing a team getting asked to do a lot more than they have been able to accomplish historically
Cumulative Flow
28/10/23
SE ZG544 S1-23-24 Agile software processes
Source: Agile Metrics in Action: How to measure and improve team performance by Christopher W. H. Davis , Published by Manning Publications, 2015

## Slide 23
Example - Combination of data
28/10/23
SE ZG544 S1-23-24 Agile software processes
Spikes in this data point can indicate potential problems:
There’s a communication gap somewhere on the team.
Completion criteria (a.k.a. done) are not defined clearly to everyone on the team.
Tasks are being rushed, usually due to pressure to hit a release date.
Source: Agile Metrics in Action: How to measure and improve team performance by Christopher W. H. Davis , Published by Manning Publications, 2015

## Slide 24
  There isn’t a silver-bullet metric that will tell you if your agile teams are performing as well as they can.
  Collecting and analyzing data in the form of metrics is an objective way to learn more about your team and a way to measure any adjustments you decide to make to your team’s behavior.
COLLECT, MEASURE, REACT, REPEAT—THE FEEDBACK LOOP
28/10/23
SE ZG544 S1-23-24 Agile software processes
Source: Agile Metrics in Action: How to measure and improve team performance by Christopher W. H. Davis , Published by Manning Publications, 2015

## Slide 25
Figuring out what matters
(X is what you want to answer; some combination of your data can get you there.)
28/10/23
SE ZG544 S1-23-24 Agile software processes
Mind mapping is a brainstorming technique where you start with an idea and then keep deconstructing it until it’s broken down into small elements. XMind (www.xmind.net/),
Source: Agile Metrics in Action: How to measure and improve team performance by Christopher W. H. Davis , Published by Manning Publications, 2015

## Slide 26
Project performance data
28/10/23
SE ZG544 S1-23-24 Agile software processes
Data is all over the place without a unified view
Questions you can answer with data from systems in your SDLC.
Adding data together to answer high-level questions
Source: Agile Metrics in Action: How to measure and improve team performance by Christopher W. H. Davis , Published by Manning Publications, 2015

## Slide 27
Thank you
28/10/23
SE ZG544 S1-23-24 Agile software processes