## Slide 1: Module 9 Part 1 Management and Governance
Harvinder S Jabbal
SSZG653 Software Architectures

## Slide 2
Management and Governance

## Slide 3
Planning
Organizing
Implementing
Measuring
Governance
Summary
Outline

## Slide 4
The planning for a project proceeds over time.
There is an initial plan that is necessarily top-down to convince upper management to build this system and give them some idea of the cost and schedule.
This top-down schedule is inherently going to be incorrect, possibly by large amounts.
Once the system has been given a go-ahead and a budget, the architecture team is formed and produces an initial architecture design.
Planning

## Slide 5
The Planning Process

## Slide 6
A top down schedule is needed to enable management to decide whether to do the project and to allocate resources.
Example: For a medium size project (~150K SLOC)
  Number of components to be estimated: ~150
  Paper design time per component: ~4 hours
  Time between engineering releases: ~8 weeks
  Overall project development allocation:
    40 percent design: 5 percent architectural, 35 percent detailed
    20 percent coding
    40 percent testing
Top Down Schedule

## Slide 7
An architecture team is created and they develop the first level decomposition of the architecture.
Each member of the architecture team will be the lead architect for each major subsystem.
A bottom up schedule is created by the architecture team
  Typically more accurate than the top down schedule
  The top down and the bottom up schedules must be reconciled to produce final (initial) schedule.
Software development plan is written that specifies releases dates and features per release. This plan guides the initial activities of the project.
Remaining Planning Steps

## Slide 8
Division of responsibilities between project manager and software architect
Global Software Development
Organizing

## Slide 9
This is the most important working relationship on the team.
The people in each role—PM and SA—must
  Respect each other
  Coordinate
  Stick to their respective spheres.
Project Manager and Software Architect

## Slide 10
Published by the Project Management Institute
ANSI and IEEE standard
Process groups
The five process groups are:
  Initiating.
  Planning.
  Executing.
  Monitoring and Controlling.
  Closing.
Project Management Body of Knowledge (PMBOK)

## Slide 11
processes performed to define a new project or a new phase of an existing project
obtaining authorization to start the project or phase.
Initiating:

## Slide 12
Those processes required to establish the scope of the project, refine the objectives, and define the course of action required to attain the objectives that the project was undertaken to achieve.
Planning:

## Slide 13
Those processes performed to complete the work defined in the project management plan to satisfy the project specifications
Executing:

## Slide 14
Those processes required to track, review, and regulate the progress and performance of the project;
Identify any areas in which changes to the plan are required; and initiate the corresponding changes.
Monitoring and Controlling:

## Slide 15
Those processes performed to finalize all activities across all Process Groups to formally close the project or phase.
Closing:

## Slide 16
Published by the Project Management Institute
ANSI and IEEE standard
Ten project management knowledge areas
  Project Integration Management.
  Project Scope management.
  Project Schedule Management.
  Project Cost Management.
  Project Quality Management.
  Project Resource Management.
  Project Communications Management.
  Project Risk Management.
  Project Procurement Management.
  Project Stakeholder Engagement.
Project Management Body of Knowledge (PMBOK)

## Slide 17
Ensuring that the various elements of the project are properly coordinated. The processes and activities needed to identify, define, combine, unify, and coordinate the various processes and project management activities within the project management process groups.
Developing, overseeing, and updating the project plan. Managing change control process.
  PM: Organizes project, manages resources, budgets and schedules. Defines metrics and metric collection strategy. Oversees change control process.
  SA: Creates design and organizes team around design. Manages dependencies. Implements the capture of the metrics. Orchestrates requests for changes. Ensures that appropriate IT infrastructure exists.
Integration Management

## Slide 18
Ensuring that the project includes all of the work required and only the work required.
Requirements
  PM: Negotiates project scope with marketing and software architect.
  SA: Elicits, negotiates, and reviews run time requirements and generate development requirements. Estimates cost, schedule, and risk of meeting requirements.
Scope Management

## Slide 19
Ensuring that the project completes in a timely fashion.(Time Management in PMBOK6)
Work breakdown structure and completion tracking. Project network diagram with dates.
  PM: Oversees progress against schedule. Helps define work breakdown structure. Schedule coarse activities to meet deadlines.
  SA: Helps define work breakdown structure. Defines tracking measures. Recommends assignment of resources to software development teams.
Schedule Management

## Slide 20
Ensuring that the project is completed within the approved budget.
Planning, estimating, budgeting, financing, funding, managing, and controlling costs.
  PM: Calculates cost to completion at various stages, makes decisions regarding build/buy and allocation of resources.
  SA: Gathers costs from individual teams, makes recommendations regarding build/buy and resource allocations.
Cost Management

## Slide 21
Determine quality policies, objectives, and responsibilities ensuring that the project will satisfy the needs for which it was undertaken.
Quality & Metrics
  PM: Defines productivity, size, and project-level quality measures.
  SA: Designs for quality and tracks system against design. Defines code-level quality metrics.
Quality Management

## Slide 22
Organise, manage and lead ensuring that the project makes the most effective use of the people involved with the project.(Human Resource Management in PMBOK6)
Managing people and their careers
  PM: Maps skill sets of people against required skill sets. Ensures that appropriate training is provided. Monitors and mentors career paths of individuals. Authorizes recruitment.
  SA: Defines required technical skill sets. Mentors developers about career paths. Recommends training. Interviews candidates.
Resource Management

## Slide 23
Ensuring timely and appropriate planning, collection, creation, distribution, storage, retrieval, management, control, monitoring, and the ultimate disposition of project information.
Communicating
  PM: Manages communication between team and external entities. Reports to upper management.
  SA: Ensures communication and coordination among developers. Solicits feedback as to progress, problems, and risks.
Communications Management

## Slide 24
conducting risk management planning, identification, analysis, response planning, and controlling risk on a project.
Risk Management
  PM: Prioritizes risks, reports risks to management, takes steps to mitigate risks.
  SA: Identifies and quantifies risks, adjusts architecture and processes to mitigate risk.
Risk Management

## Slide 25
Purchase or acquire products, services, or results needed from outside the project team. Processes in this area include Procurement Planning, Solicitation Planning, Solicitation, Source Selection, Contract Administration, and Contract Closeout.
Technology
  PM: Procures necessary resources. Introduces new technology.
  SA: Determines technology requirements. Recommends technology, training, and tools.
Procurement Management

## Slide 26
The processes required to identify all people or organizations impacted by the project, analyzing stakeholder expectations and impact on the project, and developing appropriate management strategies for effectively engaging stakeholders in project decisions and execution.
PM- Assess key participants and how the project affects their problems and needs.
SA- Ensure the stakeholders’ needs and concerns are dealt with appropriately.
Project Stakeholder Engagement

## Slide 27
Each of the ten knowledge areas contains the processes that need to be accomplished within its discipline in order to achieve effective project management.
Each of these processes also falls into one of the five process groups, creating a matrix structure such that every process can be related to one knowledge area and one process group.
Processes/Activities – Knowledge Areas.

## Slide 28
A very common development context.
Driven by
  (Labor) costs
  Skill sets and labor availability.
  Local knowledge of markets.
Global development means that coordination among teams is critical.
Global Software Development

## Slide 29
If there is a dependency between two modules, the teams assigned to those modules must coordinate over the shared interfaces.
Team Coordination Induced by Module Interaction
Coordination
Module A
Team A
Dependency
Module B
Team B

## Slide 30
Local coordination can be informal and spontaneous.
Remote coordination must be more structured.
Coordination mechanisms:
  Documentation
  Meetings
  Electronic media
Coordination

## Slide 31
Trade-offs
Incremental development
Tracking progress
Implementation Issues

## Slide 32
Software architect makes trade-offs among various quality attributes.
Project manager makes trade-offs among
  Features
  Schedule
  Quality
Project manager should resist creeping functionality (scope creep)
  Affects schedule
  Can use a Change Control Board to manage (typically slow down) the pace of changes
Trade-offs

## Slide 33
A release may be in one of three states
  Planning
  Development
  Test and repair
All three states can be simultaneously active for different releases.
Incremental Development

## Slide 34
Progress can be tracked through
  Personal contact (doesn’t scale)
  Meetings
  Metrics
  Risk management
Meetings
  Expensive use of time
  Either status or working – do not intermix
  One output of status meetings should be risks
Risks have
  Cost if they occur
  Likelihood of their occurrence
Project manager prioritizes risks
Tracking Progress

## Slide 35
Metrics are an important tool for project managers. They enable the manager to have an objective basis both for their own decision making and for reporting to upper management on the progress of the project.
Metrics can be global—pertaining to the whole project—or they may depend on a particular phase of the project.
Measuring

## Slide 36
Global metrics aid the project manager in obtaining an overall sense of the project and tracking its progress over time.
Some example metrics, that any project should capture:
  Size
  Schedule deviation
  Developer productivity
  Defects
Metrics should be tracked both historically for the organization and for the specific project.
Global Metrics

## Slide 37
Phase metrics
  Open issues
  Unmitigated risks
Cost to complete
  Bottom-up metric
    Responsibility of lead architect for each subsystem team
Phase Metrics and Cost to Complete

## Slide 38
Four responsibilities of a governing board
  Implementing a system of controls over the creation and monitoring of all architectural components and activities, to ensure the effective introduction, implementation, and evolution of architectures within the organization.
  Implementing a system to ensure compliance with internal and external standards and regulatory obligations.
  Establishing processes that support effective management of the above processes within agreed parameters.
  Developing practices that ensure accountability to a clearly identified stakeholder community, both inside and outside the organization.
Governance

## Slide 39
A project must be planned, organized, implemented, tracked, and governed.
  Top-down schedule based on size
  Bottom-up schedule based on top level decomposition.
  Reconciliation of two schedules is the basis for the software development plan.
Teams are created based on the software development plan.
The software architect and the project manage must coordinate to oversee the implementation.
Global development creates a need for an explicit coordination strategy.
Management trade offs are between schedule, function, and cost.
Progress must be tracked.
Larger systems require formal governance mechanisms.
Summary